## UseCase1-Test Plan
Use Case 1 - Signed Movement Report (Functional Scope) |  |  |  | Entity Scope | Test /SQL Script |  | Static Testing |  |  |  | Functional Testing Bronze/Silver/Gold Layer (Database) | [9 empty] | Report Testing
[11 empty] | Pre-Requisites |  |  |  | Synapse
S.No | Layer | Source System/ Table Type | Table Name |  | Data Validation | SCD Type2 | Analyse/ Understand Requirements | Access Test Control DB | Access Test Env via Synapse | Access ADLS Gen2 (Container) | Check view Existence | Check view Collation | Check Pipeline Run | Check DART | Reconcilliation (Record Count) | Data Completeness | Data Correctness | Data Transformation | SCD Type2 (Update) | SCD Type2 (Delete) | Functional | NFT
1 | Bronze | Eclispse (Incremental) | dbo_Policy | Y |  |  | ü | ü | ü | ü | ü |  | ü | ü | ü | ü | ü | N/A | ü | ü
2 |  |  | dbo_Org | Y | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | ü | ü
3 |  |  | dbo_PolicyOrg | Y | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | ü | ü
4 |  |  | dbo_LloydsBroker | Y | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | ü | ü
5 |  |  | dbo_ApplicationUser | Y | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | ü | ü
6 |  |  | dbo_PolicyLine | Y | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | ü | ü
7 |  |  | dbo_PolicyLimit | Y | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | ü | ü
8 |  |  | dbo_PolicyPrem | N | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | ü | ü
9 |  |  | dbo_FinTransCategory | N | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | ü | ü
10 |  |  | dbo_ReportingClass | N | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | ü | ü
11 |  |  | dbo_PolicyDeduction | N | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | ü | ü
12 |  |  | dbo_FinTransCategoryRole | N | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | ü | ü
15 |  | MDM/ Profisee (Full Refresh) | Syndicate | N | [6 empty] | ü | ü | ü | ü | ü | ü | ü | N/A | N/A | N/A
|  |  | Ref_SourceSystem | Y
16 |  |  | Ref_GroupDivision | Y | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | N/A | N/A
17 |  |  | Ref_GroupClass | Y | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | N/A | N/A
|  |  | Ref_BusinessClass | Y
18 |  |  | PIM Exchange Rate | N | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | N/A | N/A
19 |  |  | VelocityCoverageItem | N | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | N/A | N/A
20 |  |  | Ref_GroupPortfolio | Y | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | N/A | N/A
21 |  |  | DeductionType | N | [6 empty] | ü | ü |  |  | ü | ü | ü | N/A | N/A | N/A
28 | Silver | [9 empty] | ü |  | ü | ü | ü | ü | ü | ü | N/A | N/A
29 |  |  | Entities will be populated later | [7 empty] | ü |  |  |  | ü | ü | ü | ü | N/A | N/A
33 | [10 empty] | ü |  |  |  | ü | ü | ü | ü | N/A | N/A
34 | [10 empty] | ü |  |  |  | ü | ü | ü | ü | N/A | N/A
35 | Gold | Dim | [8 empty] | ü |  | ü | N/A | ü | ü | ü | ü | ü | ü
37 |  | Fact | Entities will be populated later | [7 empty] | ü |  |  |  | ü | ü | ü | ü | ü | ü
39 |  | Bridge | [8 empty] | ü |  |  |  | ü | ü | ü | ü | ü | ü
28 | Scenario's |  | Initial Load (INSERT)
29 |  |  | Incremental/Delta Load (UPSERT)
30 |  |  | SCD Type 2 - Update
31 |  |  | SCD Type 2 - Delete
32 | Report (if any) |  | Layout & Design as per specification | [17 empty] | ü
33 |  |  | Check all Filters/Drop down list if any | [17 empty] | ü
34 |  |  | Check all buttons if any | [17 empty] | ü
35 |  |  | Functional testing No.of records Validate measures against DB Visual Layer/Tab order | [17 empty] | ü
ü
36 | [20 empty] | ü
37 |  |  | Non-Functional Testing - Accessibility via cross browser - Perfomance based on data volume | [18 empty] | ü
38 | [21 empty] | ü
39 | [21 empty] | ü
42 | Non-Functional & Performance |  | Volume & Performance - via DB Volume & Performance - via API Performance - Report (if any) Synapse Pipelines - Duration Synapse Pipelines - Failed Point |  | Overall performance testing for allthe Data pipelines/Data Ingestion process via direct access and API call & Re-run the Data pipeline to make sure that, process will pick it up from Failed point

## QAWork - SIT Schedule
High Level E2E/SIT Schedule for MDP - Use Case1 Signed Movement Report (Currently only for Bronze Layer)
Layer | Source System | Task Details | Test Script Preparation Status | By Who | Comments/ Target Date
Pre-Requisites Check Point/ PRE SIT |  | Check the TST environment access
Access TST Control database
Check ADLS Gen2 storage account access
Check QAData database and qadata container
Check qadata container access in ADLS Gen2
Check Pipeline Run status including DART
Bronze | Eclipse | Data Validation Script | Completed | Ram | 31/10/2022
|  | Data Validation Script - Policy | WIP | Ram | Expected to be completed by 04/11/2022
|  | SCD Type2 Script | WIP | Ram | Expected to be completed by 07/11/2022
|  | Low Level Test Plan | Completed | Ram | 31/10/2022
|  | Test Case design - Data validation | WIP | Ram | Expected to be completed by 04/11/2022
|  | Test Case design - SCD Type2 | To be Done | Ram | Expected to be completed by 07/11/2022
|  | Test Case design - Delete | To be Done | Ram | Expected to be completed by 04/11/2022
|  | Test Data Preparation | To be Done | Ram | To be in touch with Eclipse owner
|  | Test Execution | To be Done | Ram | Will be ready well before end of Sprint 4
| Profisee | Understand/Analyse requirement | To be Done | Sumit
|  | Data Validation Script | To be Done | Sumit | Sumit arranged a call with Data engineers to discuss about Profisee source system details and will be decided based on the outcome
|  | SCD Type2 Script | To be Done | Sumit
|  | Test Case design - Data validation | To be Done | Sumit
|  | Test Case design - SCD Type2 | To be Done | Sumit | In-Scope ( later)
|  | Test Case to check the view existence | To be Done | Sumit | In-Scope
|  | Test Data Preparation | To be Done | Sumit | In-Scope
|  | Test Execution | To be Done | Sumit | In-Scope
Silver | Details to be added | Understanding Mapping | To be Done | Ram | Awaiting document
|  | Develop Test script - Each Entity in scope | To be Done | Ram
|  | SCD Type2 Script | N/A |  | There is no SCD type 2 behaviour for Silver Layer
|  | Test Case Design | To be Done | Ram
|  | Test Execution | To be Done
Gold | Details to be added | Understanding Mapping - Dim/Fact/Bridge | To be Done |  | Awaiting document
|  | Develop Test script - Each Entity in scope | To be Done
|  | SCD Type2 Script | To be Done
|  | Test Case Design | To be Done
|  | Test Execution | To be Done
Non-Functional (Limited Scope) |  |  | To be Done
To be Done
To be Done
To be Done
To be Done